## Planning
Planning Year 1: 08/2021 - 06/2022
Task | Responsible | Partners | Status | Explain results from column A | Year 1: 08/2021-06/2022
[5 empty] | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | June | July | Aug
Analyze the Needs, Challenges and Strengths
Perform a Strength, Weakness, Opportunity, Threat (SWOT) analysis of your program | e.g. Project Director, Project Coordinator, all staff | bar: Year 1: 08/2021-06/2022 Aug
Evaluate the progress and document your readiness and needs for this new phase of establishing a program focused on creating community-clinical linkages
Identify Model, Extent and Details of School-Based/Linked Program
Perform an Environmental Scan of the existing providers at schools and establish alignments, data sharing agreements, etc. (e.g. Federally Qualified Health Centers (FQHC))
Develop the goals and objectives for the program. Write your Specific, Measurable, Achievable, Realistic, Time-Bound (SMART) objectives
Develop partnerships with schools, school nurses and Superintendents
Identify your model: School-Based or School-Linked (or a combination of the models in different schools) and the scope of services
Identify schools, grades, the plan for gradual expansion and the scope of services (if other services are being provided onsite)
Design an early prevention program (e.g. Tooth Brushing Programs in Pre-K, Oral Health Education)
Plan staffing: volunteers or providers in the community (Private, Community Clinics, Commercial Dental Providers, etc)
Plan for and purchase equipment needed
Think through cost, billing and sustainability of your program
Engage Dental Providers
Develop an Environmental Scan of existing providers at schools and establish alignments (e.g. Federally Qualified Health Centers (FQHC), clinics, private practitioners)
Use innovative ways to involve providers and sustain the efforts: RDHAPs, Federally Qualified Health Centers (FQHC), Fee-for-Service (FFS) Dental providers
Increase the pool of providers accepting Medi-Cal
Plan for Dental Referral Management System
Identify users and setting that it will be used
Identify capacity to work at the school/community level
Identify settings and organizations interested in being involved
Align with Care Coordination Models
Identify internal partners including Maternal, Child & Adolescent Health (MCAH) and ​​​​Child Health and Disability Prevention Program (CHDP)
Identify external partners including agencies utilizing Community Health Workers workforce, Family Resource Centers, First 5, Women, Infants, and Children (WIC), etc.
Create strategies to strengthen partnerships and align efforts in Care Coordination
Identify your model of referral management
Develop a Roll-Out Plan
Identify an initial plan
Identify plan for expansion: setting up for the long term success of implementation
Identify incremental 5 year goals
Develop a Logic Model
Develop Specific, Measurable, Achievable, Realistic, Time-Bound (SMART) objectives
Develop a logic model based on the assessment above
Plan for Sustainability
Identify inter-departmental, local and state-wide resources
Gather data to be ready for funding opportunities
Develop PerformanceMeasures and Quality Improvement (QI) Approaches
Identify Performance Measures you would like to incorporate
Identify QI strategies to improve performance